## 1st
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE IRA UTILIZATION
FIRST QUARTER, CY 2020
CUYAPO, NUEVA ECIJA
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | Any
Economic Development
Dev't. of Walkway - Market |  | 3000000 |  |  | 99.87% | 2996082.34
Road concreting Bonifacio-San Juan |  | 2200000 |  |  | 49.96% | 1099143.41
Road concreting Luna |  | 2000000 |  |  | 99.92% | 1998393.58
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CAROLINA C. UMIPIG | [5 empty] | FLORIDA P. ESTEBAN, M.D
Municipal Budget Officer | [5 empty] | Local Chief Executive

## 2nd
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE IRA UTILIZATION
SECOND QUARTER, CY 2020
CUYAPO, NUEVA ECIJA
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | Any
Economic Development
Dev't. of Walkway - Market |  | 3000000 |  |  | 99.87% | 2996082.34
Road concreting Bonifacio-San Juan |  | 2200000 |  |  | 99.92% | 2198286.82
Road concreting Luna |  | 2000000 |  |  | 99.92% | 1998393.58
Construction of Bonifacio Brgy. Hall |  | 2498531.38 |  |  | 70% | 1748972
Rehab of CanalPublic Market |  | 2597830.18 |  |  | 61.59% | 1600000
Construction of San Juan SWIP |  | 5990877.33 |  |  | 50% | 2995441.01
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CAROLINA C. UMIPIG | [5 empty] | FLORIDA P. ESTEBAN, M.D
Municipal Budget Officer | [5 empty] | Local Chief Executive

## 3rd
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE IRA UTILIZATION
THIRD QUARTER, CY 2020
CUYAPO, NUEVA ECIJA
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | Any
Economic Development
Dev't. of Walkway - Market |  | 3000000 |  |  | 99.87% | 2996082.34
Road concreting Bonifacio-San Juan |  | 2200000 |  |  | 99.92% | 2198286.82
Road concreting Brgy. Villaflores |  | 923415.45 |  |  | 100% | 923415.45
Road concreting Luna |  | 2000000 |  |  | 99.92% | 1998393.58
Road concreting Calancuasan Sur |  | 971134.8 |  |  | 100% | 971134.8
Construction of Bonifacio Brgy. Hall |  | 2498531.38 |  |  | 100% | 2498531.38
Rehab of Canal Public Market |  | 2597830.18 |  |  | 61.59% | 1600000
Construction of San Juan SWIP |  | 5990877.33 |  |  | 50% | 2995441.01
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CAROLINA C. UMIPIG | [5 empty] | FLORIDA P. ESTEBAN, M.D
Municipal Budget Officer | [5 empty] | Local Chief Executive
Nagcuralan |  | 2000000 |  |  | 100% | 2000000
Bambanaba (Sitio Cabangaran) |  | 2000000 |  |  | 100% | 2000000
District V |  | 800000 |  |  | 100% | 800000
Piglisan -Loob |  | 2800000 |  |  | 100% | 2800000
Ungab(Sitio Pao) |  | 1000000 |  |  | 100% | 1000000
Environmental Dev't.
Clean & Green Program |  | 413257 |  |  | 32.13% | 132800
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CAROLINA C. UMIPIG | [5 empty] | FLORIDA P. ESTEBAN, M.D
Municipal Budget Officer | [5 empty] | Local Chief Executive

## 4th
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE IRA UTILIZATION
FIRST QUARTER, CY 2020
CUYAPO, NUEVA ECIJA
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | Any
Social Development
Rehab & Dev't. of Mun. Park |  | 3000000 |  |  | 100% | 3000000
Rehab of Mt.Bulaylay |  | 1000000 |  |  | 14.82% | 148169
Construction of Solar Powered Potable Water
Sabit (Rest Stop) |  | 1000000 |  |  | 100% | 1000000
Colosboa |  | 2000000 |  |  | 100% | 2000000
Market |  | 3000000 |  |  | 100% | 3000000
Economic Development
Amortization to LBP |  | 5400000 |  |  | 87.42% | 4720433.71
Purchase of Mat. To various brgys. |  | 350000 |  |  | 92.82% | 324887
Purchase of Farm Tractor |  | 1000000 |  |  | 100% | 1000000
LGU Counterpart Kalit litan SWIP (Baloy) |  | 1200000 |  |  | 100% | 1200000
Road concreting of various brgys.
San Antonio |  | 3000000 |  |  | 100% | 3000000
Calancuasan Sur (Purok 5 & 6) |  | 2000000 |  |  | 100% | 2000000
Tutuloy-Loob |  | 4000000 |  |  | 100% | 4000000
Nagcuralan |  | 2000000 |  |  | 100% | 2000000
Bambanaba (Sitio Cabangaran) |  | 2000000 |  |  | 100% | 2000000
District V |  | 800000 |  |  | 100% | 800000
San Jose to Dist. IV |  | 1000000 |  |  | 100% | 1000000
Piglisan -Loob |  | 2800000 |  |  | 100% | 2800000
Ungab(Sitio Pao) |  | 1000000 |  |  | 100% | 1000000
Environmental Dev't.
Clean & Green Program |  | 413257 |  |  | 32.13% | 132800
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CAROLINA C. UMIPIG | [5 empty] | FLORIDA P. ESTEBAN, M.D
Municipal Budget Officer | [5 empty] | Local Chief Executive