## 1st
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE IRA UTILIZATION
FIRST QUARTER, CY 2020
CUYAPO, NUEVA ECIJA
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | Any
Economic Development
Dev't. of Walkway - Market |  | 3000000 |  |  | 99.87% | 2996082.34
Road concreting Bonifacio-San Juan |  | 2200000 |  |  | 49.96% | 1099143.41
Road concreting Luna |  | 2000000 |  |  | 99.92% | 1998393.58
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CAROLINA C. UMIPIG | [5 empty] | FLORIDA P. ESTEBAN, M.D
Municipal Budget Officer | [5 empty] | Local Chief Executive

## 2nd
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE IRA UTILIZATION
SECOND QUARTER, CY 2020
CUYAPO, NUEVA ECIJA
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | Any
Economic Development
Dev't. of Walkway - Market |  | 3000000 |  |  | 99.87% | 2996082.34
Road concreting Bonifacio-San Juan |  | 2200000 |  |  | 99.92% | 2198286.82
Road concreting Luna |  | 2000000 |  |  | 99.92% | 1998393.58
Construction of Bonifacio Brgy. Hall |  | 2498531.38 |  |  | 70% | 1748972
Rehab of CanalPublic Market |  | 2597830.18 |  |  | 61.59% | 1600000
Construction of San Juan SWIP |  | 5990877.33 |  |  | 50% | 2995441.01
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CAROLINA C. UMIPIG | [5 empty] | FLORIDA P. ESTEBAN, M.D
Municipal Budget Officer | [5 empty] | Local Chief Executive

## 3rd
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE IRA UTILIZATION
THIRD QUARTER, CY 2020
CUYAPO, NUEVA ECIJA
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | Any
Social Development
Installation of St. Light Sn Jose to Curva |  | 1500000 |  |  | 100% | 1500000
Cemetery Dev't. |  | 2000000 |  |  | 100% | 2000000
Economic Development
Dev't. of Walkway - Market |  | 3000000 |  |  | 99.87% | 2996082.34
Road concreting Bonifacio-San Juan |  | 2200000 |  |  | 99.92% | 2198286.82
Road concreting Luna |  | 2000000 |  |  | 99.92% | 1998393.58
Road concreting Sta. Cruz |  | 2493190.06 |  |  | 100% | 2493190.06
Road concreting Nagcuralan |  | 1720318.76 |  |  | 100% | 1720318.76
Road concreting Bambanaba to Sta. Cruz |  | 2493190.06 |  |  | 100% | 2493190.06
Construction of Bonifacio Brgy. Hall |  | 2498531.38 |  |  | 100% | 2498531.38
Rehab of Canal District IV |  | 400566 |  |  | 100% | 400566
Rehab of Canal District V |  | 1396771.03 |  |  | 100% | 1396771.03
Environmental Dev't.
Purchase of Machinery for waste processing |  | 330000 |  |  | 100% | 330000
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CAROLINA C. UMIPIG | [5 empty] | FLORIDA P. ESTEBAN, M.D
Municipal Budget Officer | [5 empty] | Local Chief Executive

## 4th
FDP Form 7 - 20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF THE IRA UTILIZATION
FOURTH QUARTER, CY 2020
CUYAPO, NUEVA ECIJA
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost Incurred | Extensions, if | Remarks
|  |  |  | Date | Completion | to Date | Any
Social Development
Installation of St. Light Sn Jose to Curva |  | 1500000 |  |  | 99.63% | 1494523.36
Economic Development
Amortization of Loan LBP |  | 8305141.79 |  |  | 100% | 8304750.81
Dev't. of Walkway - Market |  | 3000000 |  |  | 99.87% | 2996082.34
Construction of Bonifacio Brgy. Hall |  | 2500000 |  |  | 99.94% | 2498531.38
Cemetery Dev't. |  | 2000000 |  |  | 99.81% | 1996144.55
Road concreting Bambanaba to Sta. Cruz |  | 2500000 |  |  | 99.73% | 2493190.06
Road concreting Bonifacio-San Juan |  | 2200000 |  |  | 99.92% | 2198286.82
Road concreting Luna |  | 2000000 |  |  | 99.92% | 1998393.58
Road concreting Sta. Cruz |  | 2500000 |  |  | 99.73% | 2493190.06
Road concreting Nagcuralan |  | 1725000 |  |  | 99.73% | 1720318.76
Road concreting Calancuasan Norte |  | 1000000 |  |  | 87.63% | 876281.88
Road concreting Calancuasan Sur (Purok 5) |  | 1000000 |  |  | 97.11% | 971134.8
Construction of San Juan SWIP |  | 5990877.33 |  |  | 90.06% | 5395438.67
Environmental Dev't.
Purchase of Machinery for waste processing |  | 3300000 |  |  | 99.09% | 3270000
Rehab of Canal District V |  | 1396771.03 |  |  | 100% | 1396771.03
Rehab of Canal District IV |  | 400566 |  |  | 100% | 400566
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
CAROLINA C. UMIPIG | [5 empty] | FLORIDA P. ESTEBAN, M.D
Municipal Budget Officer | [5 empty] | Local Chief Executive